PROJECT CHARTER

Project NOVA

AI-Powered Self-Improvement & AI BA Portfolio System

Version 1.1  |  Issued: April 27, 2026  |  Updated: April 27, 2026 (RACI revision)

| Field | Value |
| --- | --- |
| Project Name | NOVA |
| Project Owner / BA | Shrutika |
| Project Type | Personal Agile Initiative (Scrum) |
| Start Date | April 27, 2026 |
| End Date | June 26, 2026 |
| Duration | 60 days / 6 sprints of 10 days each |
| Time Commitment | 5 hrs/day × 5 working days/week (~25 hrs/wk) |
| Total Project Hours | ~215 hours |
| Working Days | Monday – Friday |
| Buffer Days | Saturday & Sunday (optional work allowed) |
| Primary Tools | Google Sheets (Layer 1), n8n, Python, Streamlit, Claude API, GitHub |

# 1. Project Purpose

NOVA is a dual-purpose AI-powered system designed to serve two interconnected objectives:

## 1.1 Personal Tool

Systematically address the recurring pattern of strong initial effort followed by difficulty maintaining consistency across personal habits — including morning routines, fitness, reading, and continuous learning — by introducing structured tracking, automated nudges, and AI-driven feedback loops.

## 1.2 Portfolio Project

Convert existing AI/ML and prompt-engineering knowledge (Georgian College PG Certificate, Master's in CS, hands-on prompt engineering) into recruiter-visible Business Analyst artifacts. NOVA itself is the artifact: a full Agile delivery led by Shrutika as BA in partnership with an AI Project Manager (Claude), evidencing senior-level AI BA capability — requirements, process design, AI integration, stakeholder communication, and outcome measurement.

## 1.3 Job Opportunity Radar (Stretch Module)

Within the AI integration layer, NOVA includes a Job Opportunity Radar that scrapes/monitors postings from LinkedIn, Indeed, Glassdoor, and company career sites, scores them against the user profile via Claude API, drafts tailored cover letter snippets and resume bullets, and surfaces a ranked daily top-10 list. The user reviews and submits applications manually (no automated submission, due to platform Terms of Service).

# 2. Problem Statement

Two parallel inefficiencies are addressed:

- Personal: Strong initial motivation across new habits is consistently followed by inconsistency by week 3-4, preventing compounding gains in fitness, learning, and routine quality.

- Professional: Substantial AI/ML and prompt-engineering knowledge exists but is not currently packaged into BA artifacts that hiring managers can evaluate, slowing the transition into Senior AI BA roles in the Toronto financial services market.

NOVA addresses both by making the act of building the consistency-tracking system itself the portfolio evidence of senior AI BA capability.

# 3. Vision Statement

On June 26, 2026, NOVA will be a fully functional AI-augmented system delivering measurable improvements in daily productivity and consistency, while serving as a public-facing portfolio artifact that evidences Senior AI BA capability to recruiters and hiring managers in the Toronto financial services market.

# 4. Success Metrics

All metrics are SMART (specific, measurable, achievable, relevant, time-bound) and reviewed at every Sprint Review.

| Success Metric | Target | Measurement Cadence | Owner / Source of Truth |
| --- | --- | --- | --- |
| Days logged in NOVA out of 60 | ≥ 70 % (≥ 42 days) | Daily | Google Sheets log |
| AI BA artifacts produced | 15 | Per sprint | GitHub repo |
| LinkedIn / GitHub case studies published | 3 | Per major milestone | LinkedIn + GitHub |
| Job applications referencing NOVA | 30 | Weekly | Application tracker tab |
| Hours of focused learning logged | 100 | Daily | Learning log tab |

# 5. Scope

## 5.1 In Scope

| In-Scope Item | Description |
| --- | --- |
| Skills Development pillar | Sprints 1-4: learning logs, AI BA artifact log, weekly summary auto-generation |
| Habit Formation pillar (lite) | Sprint 5: simple habit-streak tracking integrated with Skills Dev |
| Layer 1 — Data capture | Google Sheets workbook with structured tabs and validations |
| Layer 2 — Automation | n8n workflows: daily log reminders, weekly summary trigger, opportunity scrape |
| Layer 3 — Analytics | Python scripts for streak detection, learning-velocity charts, artifact ROI |
| Layer 4 — AI insights UI | Streamlit dashboard powered by Claude API (insights, summaries, prioritization) |
| Job Opportunity Radar | Scrape, score, draft tailored cover-letter snippets; manual submission only |
| Portfolio outputs | 1 GitHub repo, 3 LinkedIn case studies, 1 architecture diagram, 1 demo video |

## 5.2 Out of Scope

| Out-of-Scope Item | Reason |
| --- | --- |
| Wellness pillar (full) | Deferred to post-launch v2 |
| Productivity pillar (full) | Deferred to post-launch v2 |
| Mobile application | Streamlit web dashboard sufficient for v1 |
| Multi-user / shared accounts | Personal tool only for v1 |
| Custom-trained ML models | Claude API covers AI requirements; no training infrastructure needed |
| Automated job submission | Violates LinkedIn / Indeed / Glassdoor ToS; risks account bans |
| Native integrations beyond Sheets / n8n / Streamlit | Architectural simplicity prioritized for 60-day delivery |

# 6. Timeline & Sprint Plan

Six sprints of 10 calendar days (~7 working days, ~35 hours each). Each sprint follows full Scrum ceremonies: Sprint Planning (Day 1), Daily Check-ins (5 min written), Sprint Review (Day 9), Retrospective (Day 10).

| Sprint | Dates | Theme | Sprint-End Deliverable |
| --- | --- | --- | --- |
| Sprint 0 | Apr 27 – May 6 | Discovery & Foundation | Charter, full backlog, Layer 1 (Sheets) live with first entries |
| Sprint 1 | May 7 – May 16 | Skills Dev MVP | Daily learning log functional; 7+ real entries; weekly summary template |
| Sprint 2 | May 17 – May 26 | Automation Layer | n8n workflows orchestrating logs, reminders, opportunity scrape |
| Sprint 3 | May 27 – Jun 5 | Analytics Layer | Python notebooks producing streak / velocity / ROI charts |
| Sprint 4 | Jun 6 – Jun 15 | AI Insights Layer | Streamlit + Claude API dashboard; Job Opportunity Radar live |
| Sprint 5 | Jun 16 – Jun 25 | Polish, Habit Layer & Case Study | Habit-streak module added; LinkedIn case studies published; demo recorded |

# 7. Governance & Ceremonies

## 7.1 Roles

- Project Manager — Claude (planning, sprint management, accountability, risk management, ceremony facilitation, status reporting)

- Product Owner — Shrutika (priorities, accept / reject sprint output)

- Business Analyst — Shrutika (requirements, user stories, acceptance criteria, process flows, stakeholder engagement)

- Developer — Shrutika (build, integrate, test)

- Tester / UAT — Shrutika (validate acceptance criteria with real data)

- Stakeholder — Shrutika as job-seeker (the end-user persona)

## 7.2 Ceremonies

| Ceremony | Duration | Purpose |
| --- | --- | --- |
| Sprint Planning | 60 min | Pull stories from Product Backlog into Sprint Backlog; commit |
| Daily Check-in | 5 min | Written: yesterday / today / blockers (logged in Sheets) |
| Sprint Review | 60 min | Demo to self; capture screenshots / clips for portfolio |
| Retrospective | 45 min | What worked, what didn't, one process change for next sprint |
| Backlog Refinement | 30 min | Mid-sprint: clarify next sprint's stories |

## 7.3 Definition of Ready & Done

| Definition of Ready (story can enter sprint) | Definition of Done (story is shipped) |
| --- | --- |
| Has clear user story format (As a / I want / So that) | All acceptance criteria met |
| Has acceptance criteria (≥ 2) | Tested with real personal data (UAT pass) |
| Estimated in story points (1, 2, 3, 5, 8) | Documented in repo (README or sprint log) |
| Dependencies identified | Demoed at Sprint Review |
| BA + PO (both = Shrutika) signed off | No critical bugs / blockers open |

# 8. Risk Register

Top risks identified during charter sign-off. Re-reviewed at every Sprint Retrospective.

| # | Risk | Likelihood | Impact | Mitigation |
| --- | --- | --- | --- | --- |
| R1 | Consistency-failure pattern repeats (the meta-risk) | High | High | Wed/Sun buffer days non-negotiable; weekly retro adjusts load; minimum-viable daily commit = 1 line in Sheets |
| R2 | Scope creep into wellness / productivity pillars | High | Medium | Charter explicitly out-of-scope; PO (self) must reject mid-sprint additions |
| R3 | Technical learning curve (n8n, Streamlit, Python) | Medium | Medium | Sprint 0 includes 2-hour ramp-up per tool; small spikes before full sprint commit |
| R4 | Job-search activity competes with build time | High | Medium | Job apps logged INSIDE NOVA (turns competition into reinforcement) |
| R5 | Job Opportunity Radar scraping breaks due to site changes | Medium | Low | Build with API-first sources where available; graceful failure modes |
| R6 | Baicorp work crunch consumes capacity | Medium | Medium | 5-hr/day target is a ceiling; floor is 1 hr written reflection on no-build days |
| R7 | Loss of motivation around Sprint 3 (the danger zone) | Medium | High | Sprint 3 deliverable is intentionally visual (charts) for dopamine reward |

# 9. Constraints & Assumptions

## 9.1 Constraints

- Time budget: 5 hours/day × Mon-Fri; weekend work optional and not assumed

- Solo execution: all roles played by Shrutika

- Tooling: Google Sheets for Layer 1 (free, low setup, recruiter-shareable)

- Budget: Claude Pro subscription only; no paid SaaS for v1

- Compliance: no automated submission to job platforms

## 9.2 Assumptions

- No major Baicorp work crunches that consume entire weekday evenings

- No major personal / family blockers in May–June

- Claude API quota sufficient for ~50 calls/day during active development

- Internet, hardware, and tool licenses remain stable

# 10. Sign-Off

By signing below, the project is authorised to commence Sprint 0 on April 27, 2026.

| Role | Name | Sign-off Date |
| --- | --- | --- |
| Product Owner | Shrutika | _____________ |
| Business Analyst | Shrutika | _____________ |
| Developer | Shrutika | _____________ |

— End of Charter v1.1 —