## Read Me
Project NOVA — Tracking Workbook
Companion to Charter v1.1 · Issued April 27, 2026 · Updated April 27, 2026 (RACI revision)
How to use this workbook
1. | Open daily. Spend 5 minutes in the Daily Log tab logging yesterday/today/blockers + hours.
2. | Sprint Planning Day: copy stories from Product Backlog into the active Sprint Backlog tab.
3. | Sprint Review Day: mark stories Done, capture screenshots, update Metrics Dashboard.
4. | Sprint Retro Day: write 3 lines in Daily Log under that day's Notes column.
5. | Job Apps tab: log every application you submit. The dashboard auto-counts those referencing NOVA.
Tabs in this workbook
• | Product Backlog — every user story across all 6 sprints, prioritised, sized.
• | Sprint 0 Backlog — committed stories for Apr 27–May 6, with daily breakdown.
• | Daily Log — one row per calendar day; auto-flags consistency.
• | Metrics Dashboard — live status against the 5 SMART targets.
• | Burndown — story-point burndown for Sprint 0.
• | Risk Register — top risks with likelihood × impact.
• | Job Apps — application tracker; auto-counts NOVA-referenced apps.
Discipline rules (read aloud at every Monday standup)
→ | Wed/Sun (or Sat/Sun) buffer days are NON-NEGOTIABLE. Missing them = retro item.
→ | Floor commitment on busy days = 1 line in Daily Log. That counts as a logged day.
→ | Mid-sprint scope additions are forbidden. Park them in Product Backlog as 'Later'.
→ | If a sprint slips, descope before extending — protect the 60-day end date.
Working Environment & RACI
Added in v1.1 — formal split of project responsibilities between human BA (Shrutika) and AI Project Manager (Claude).
| Role | Person | Responsibilities
| Project Manager | Claude | Planning, sprint management, ceremony facilitation, asking the right questions, accountability, risk management, status reporting
| Product Owner | Shrutika | Priorities, accept / reject sprint output, backlog ordering
| Business Analyst | Shrutika | Requirements elicitation, user stories, acceptance criteria, process flows, stakeholder engagement (with self as end-user)
| Developer | Shrutika | Build, integrate, test
| Tester / UAT | Shrutika | Validate acceptance criteria with real personal data
| Stakeholder | Shrutika | End-user persona — the job-seeker NOVA serves
Note: When you discuss NOVA with recruiters, frame it as 'Led BA work and partnered with an AI co-pilot acting as Project Manager.' Honest, modern, and stronger than 'I did everything solo.'

## Product Backlog
Product Backlog — Project NOVA
Stories prioritized MoSCoW; estimated in story points (1, 2, 3, 5, 8). 1 SP ≈ 2 hrs. v1.1 — Owner column split by RACI.
ID | Sprint | User Story | Acceptance Criteria | SP | Priority | Status | Owner
US-001 | S0 | As the BA, I want a signed Project Charter, so that scope and goals are locked. | 1) All 10 sections complete 2) Self sign-off recorded 3) Stored in repo | 2 | Must | Done | BA: Shrutika ¦ PM: Claude
US-002 | S0 | As the BA, I want a complete Product Backlog, so that all sprints are pre-planned. | 1) ≥ 25 stories 2) Each has AC 3) Each sized in SP 4) MoSCoW priority assigned | 3 | Must | Done | BA: Shrutika ¦ PM: Claude
US-003 | S0 | As the user, I want a Google Sheets workspace with structured tabs, so that I can log data daily. | 1) 6 tabs created 2) Validations on date/numeric fields 3) First 3 days logged | 5 | Must | To Do | Shrutika (BA → Dev → Test)
US-004 | S0 | As the BA, I want a public GitHub repo, so that artifacts are recruiter-visible. | 1) README explaining NOVA 2) Charter committed 3) /docs and /src folders created | 2 | Must | To Do | Shrutika (BA → Dev → Test)
US-005 | S0 | As the user, I want a Skills Dev data model, so that learning sessions and artifacts are captured uniformly. | 1) Field list documented 2) Reviewed against 3 sample log entries 3) Stored in /docs | 2 | Must | To Do | Shrutika (BA → Dev → Test)
US-006 | S0 | As the BA, I want a Sprint 0 retrospective, so that lessons feed Sprint 1. | 1) 3 keep / 3 stop / 3 start items 2) 1 process change committed | 1 | Must | To Do | BA: Shrutika ¦ PM: Claude
US-101 | S1 | As the user, I want a daily learning-session log entry form, so that I can record what I studied in <1 minute. | 1) Form/template <1 min to fill 2) Captures topic, hours, source, key insight 3) 7 entries logged | 3 | Must | To Do | Shrutika (BA → Dev → Test)
US-102 | S1 | As the user, I want an artifact log, so that every BA artifact I produce is tracked with link & status. | 1) Captures artifact name, type, link, status, date 2) ≥ 3 real artifacts logged | 3 | Must | To Do | Shrutika (BA → Dev → Test)
US-103 | S1 | As the user, I want an automated weekly summary template, so that I can review progress in 5 minutes. | 1) Auto-counts hours, sessions, artifacts 2) Surfaces top 3 insights 3) Tested against Wk 1 data | 5 | Must | To Do | Shrutika (BA → Dev → Test)
US-104 | S1 | As the user, I want streak tracking on learning days, so that I get visual feedback on consistency. | 1) Current streak visible on dashboard 2) Longest streak tracked 3) Resets correctly after gap | 3 | Should | To Do | Shrutika (BA → Dev → Test)
US-105 | S1 | As the BA, I want Sprint 1 demo screenshots, so that they feed the LinkedIn case study later. | 1) ≥ 5 screenshots 2) Stored in /docs/screenshots/sprint1 | 1 | Should | To Do | BA: Shrutika ¦ PM: Claude
US-201 | S2 | As the user, I want an n8n workflow that emails me a daily log reminder at 9 PM, so that I don't forget to log. | 1) Reminder fires daily 2) Configurable time 3) Skips on buffer days | 3 | Must | To Do | Shrutika (BA → Dev → Test)
US-202 | S2 | As the user, I want an n8n workflow that compiles the weekly summary every Sunday, so that it lands in my inbox. | 1) Triggers Sunday 6 PM 2) Pulls from Sheets 3) Email arrives with formatted summary | 5 | Must | To Do | Shrutika (BA → Dev → Test)
US-203 | S2 | As the user, I want a basic job-posting scraper for one source (Indeed CA), so that I have a daily candidate list. | 1) Scrapes Senior AI BA, Toronto 2) Stores top 10 3) Respects rate limits | 5 | Must | To Do | Shrutika (BA → Dev → Test)
US-204 | S2 | As the user, I want validation on Sheets entries, so that bad data doesn't pollute the analytics layer. | 1) Date format enforced 2) Numeric fields validated 3) Required fields flagged | 2 | Should | To Do | Shrutika (BA → Dev → Test)
US-205 | S2 | As the BA, I want a Sprint 2 retro, so that automation lessons feed analytics work. | 1) 3/3/3 retro items 2) 1 process change | 1 | Must | To Do | BA: Shrutika ¦ PM: Claude
US-301 | S3 | As the user, I want a Python notebook that calculates learning velocity per week, so that I see whether I'm accelerating. | 1) Reads Sheets via API 2) Outputs weekly hours chart 3) Trend line included | 5 | Must | To Do | Shrutika (BA → Dev → Test)
US-302 | S3 | As the user, I want artifact ROI analysis, so that I know which artifact types attract recruiter responses. | 1) Joins artifact log with job-app log 2) Outputs response rate by type | 5 | Must | To Do | Shrutika (BA → Dev → Test)
US-303 | S3 | As the user, I want streak-pattern analytics, so that I understand which days/contexts I break consistency. | 1) Day-of-week breakdown 2) Average streak length 3) Top 3 break patterns | 3 | Should | To Do | Shrutika (BA → Dev → Test)
US-304 | S3 | As the BA, I want analytics outputs committed to the repo, so that recruiters see code + insights. | 1) /src/analytics/ populated 2) README updated 3) ≥ 2 charts as PNG | 2 | Must | To Do | Shrutika (BA → Dev → Test)
US-401 | S4 | As the user, I want a Streamlit dashboard with 4 tabs (Today / Trends / Artifacts / Jobs), so that everything is in one place. | 1) All 4 tabs render 2) Data refreshed on load 3) Mobile-readable | 8 | Must | To Do | Shrutika (BA → Dev → Test)
US-402 | S4 | As the user, I want Claude API to generate a daily insight from yesterday's log, so that I get coaching automatically. | 1) Insight ≤ 100 words 2) References specific entry 3) Cached to avoid re-calling | 5 | Must | To Do | Shrutika (BA → Dev → Test)
US-403 | S4 | As the user, I want the Job Opportunity Radar to score top 10 postings daily, so that I prioritize fast. | 1) Top 10 ranked 2) Score 0-100 with rationale 3) Tailored cover-letter snippet drafted | 8 | Must | To Do | Shrutika (BA → Dev → Test)
US-404 | S4 | As the BA, I want a recorded demo video (3-5 min), so that I can share NOVA in interviews. | 1) Voiceover walkthrough 2) Uploaded to YouTube unlisted 3) Linked from README | 3 | Should | To Do | Shrutika (BA → Dev → Test)
US-501 | S5 | As the user, I want a simple habit-streak module added (3 habits), so that NOVA covers the second pillar. | 1) 3 habits configurable 2) Streak per habit 3) Logged in dashboard | 5 | Must | To Do | Shrutika (BA → Dev → Test)
US-502 | S5 | As the BA, I want LinkedIn case study #1 (the discovery story), so that recruiters see BA fundamentals. | 1) ≥ 800 words 2) Includes architecture diagram 3) Published | 3 | Must | To Do | Shrutika (BA → Dev → Test)
US-503 | S5 | As the BA, I want LinkedIn case study #2 (the AI integration story), so that recruiters see AI fluency. | 1) ≥ 800 words 2) Includes Claude API examples 3) Published | 3 | Must | To Do | Shrutika (BA → Dev → Test)
US-504 | S5 | As the BA, I want LinkedIn case study #3 (the outcomes story), so that recruiters see measurable impact. | 1) ≥ 800 words 2) Includes metrics dashboard screenshot 3) Published | 3 | Must | To Do | Shrutika (BA → Dev → Test)
US-505 | S5 | As the BA, I want a polished GitHub README with badges, architecture, screenshots, so that the repo lands well. | 1) README has 6 sections 2) Architecture diagram 3) Screenshots embedded | 2 | Must | To Do | Shrutika (BA → Dev → Test)
US-506 | S5 | As the BA, I want a final retrospective and lessons-learned doc, so that NOVA's narrative is complete. | 1) Top 5 lessons 2) Top 5 wins 3) v2 backlog seeded | 2 | Must | To Do | BA: Shrutika ¦ PM: Claude

## Sprint 0 Backlog
Sprint 0 — Discovery & Foundation (Apr 27 – May 6, 2026)
Goal: Charter signed, Backlog complete, Layer 1 (Sheets) live with first entries logged. Capacity: ~35 hrs.
Day | Date | Type | Hrs | Task | Linked Story | Status
Mon | 2026-04-27 | Build | 5 | Charter sign-off + repo init + research personal-OS templates | US-001, US-004 | In Progress
Tue | 2026-04-28 | Build | 5 | Draft full Product Backlog with stories + AC + sizing | US-002 | To Do
Wed | 2026-04-29 | Buffer | 0 | BUFFER DAY — no NOVA work; rest | — | —
Thu | 2026-04-30 | Build | 5 | Design Skills Dev data model + create Sheets structure | US-003, US-005 | To Do
Fri | 2026-05-01 | Build | 5 | Finish Sheets tabs, validations, formulas; commit to repo | US-003 | To Do
Sat | 2026-05-02 | Build | 5 | Definition of Done v1; first 3 real log entries (UAT round 1) | US-003 | To Do
Sun | 2026-05-03 | Buffer | 0 | BUFFER DAY — no NOVA work; rest | — | —
Mon | 2026-05-04 | Build | 5 | UAT round 2; fix any field issues; finalize Sheets schema | US-003 | To Do
Tue | 2026-05-05 | Review | 5 | Sprint Review (self-demo + screenshots) + Retrospective | US-006 | To Do
Wed | 2026-05-06 | Buffer | 0 | BUFFER + Sprint 1 Planning prep (read US-101 to US-105) | — | —
TOTAL |  |  | 35 | Hours committed Sprint 0

## Daily Log
Daily Log — log every working day (5-min commitment minimum)
Floor commitment: 1 line. That's a logged day. Don't break the chain.
Date | Day | Sprint | Hrs | Yesterday's progress | Today's plan | Blockers / notes | Logged?
2026-04-27 | Mon | S0
2026-04-28 | Tue | S0
2026-04-29 | Wed | S0
2026-04-30 | Thu | S0
2026-05-01 | Fri | S0
2026-05-02 | Sat | S0
2026-05-03 | Sun | S0
2026-05-04 | Mon | S0
2026-05-05 | Tue | S0
2026-05-06 | Wed | S0
2026-05-07 | Thu | S1
2026-05-08 | Fri | S1
2026-05-09 | Sat | S1
2026-05-10 | Sun | S1
2026-05-11 | Mon | S1
2026-05-12 | Tue | S1
2026-05-13 | Wed | S1
2026-05-14 | Thu | S1
2026-05-15 | Fri | S1
2026-05-16 | Sat | S1
2026-05-17 | Sun | S2
2026-05-18 | Mon | S2
2026-05-19 | Tue | S2
2026-05-20 | Wed | S2
2026-05-21 | Thu | S2
2026-05-22 | Fri | S2
2026-05-23 | Sat | S2
2026-05-24 | Sun | S2
2026-05-25 | Mon | S2
2026-05-26 | Tue | S2
2026-05-27 | Wed | S3
2026-05-28 | Thu | S3
2026-05-29 | Fri | S3
2026-05-30 | Sat | S3
2026-05-31 | Sun | S3
2026-06-01 | Mon | S3
2026-06-02 | Tue | S3
2026-06-03 | Wed | S3
2026-06-04 | Thu | S3
2026-06-05 | Fri | S3
2026-06-06 | Sat | S4
2026-06-07 | Sun | S4
2026-06-08 | Mon | S4
2026-06-09 | Tue | S4
2026-06-10 | Wed | S4
2026-06-11 | Thu | S4
2026-06-12 | Fri | S4
2026-06-13 | Sat | S4
2026-06-14 | Sun | S4
2026-06-15 | Mon | S4
2026-06-16 | Tue | S5
2026-06-17 | Wed | S5
2026-06-18 | Thu | S5
2026-06-19 | Fri | S5
2026-06-20 | Sat | S5
2026-06-21 | Sun | S5
2026-06-22 | Mon | S5
2026-06-23 | Tue | S5
2026-06-24 | Wed | S5
2026-06-25 | Thu | S5

## Metrics Dashboard
Metrics Dashboard — live status against Charter targets
Metric | Target | Actual | % to Goal | Notes
Days logged in NOVA (out of 60) | 42 | 0 | 0% | Target = 70%
AI BA artifacts produced | 15 | 0 | 0% | Update manually as artifacts ship
LinkedIn / GitHub case studies | 3 | 0 | 0% | Sprint 5 deliverable
Job applications referencing NOVA | 30 | 0 | 0% | Counted from Job Apps tab
Hours of focused learning logged | 100 | 0 | 0% | Auto-summed from Daily Log
Sprint progress
Sprint | Stories | Done | % Done | Status
S0 | 6 | 2 | 33.33% | In Progress
S1 | 5 | 0 | 0% | Not Started
S2 | 5 | 0 | 0% | Not Started
S3 | 4 | 0 | 0% | Not Started
S4 | 4 | 0 | 0% | Not Started
S5 | 6 | 0 | 0% | Not Started

## Burndown
Sprint 0 Burndown — story points remaining by day
Day | Date | Ideal Remaining | Actual Remaining | Variance
Mon | 2026-04-27 | 12.86
Tue | 2026-04-28 | 10.71
Wed | 2026-04-29 | 10.71
Thu | 2026-04-30 | 8.57
Fri | 2026-05-01 | 6.43
Sat | 2026-05-02 | 4.29
Sun | 2026-05-03 | 4.29
Mon | 2026-05-04 | 2.14
Tue | 2026-05-05 | 0
Wed | 2026-05-06 | 0
Total Sprint 0 SP = 15 · Working days = 7 · Ideal burn = ~2.14 SP/day
Update column D at end of each working day with SP still remaining.

## Risk Register
Risk Register — reviewed every retrospective
# | Risk | Likelihood | Impact | Score (L×I) | Mitigation
R1 | Consistency-failure pattern repeats (the meta-risk) | High | High | 9 | Wed/Sun buffer days non-negotiable; floor commitment = 1 line in Daily Log
R2 | Scope creep into wellness / productivity pillars | High | Medium | 6 | Charter explicitly OOS; reject mid-sprint adds; park in 'v2 ideas'
R3 | Technical learning curve on n8n / Streamlit / Python | Medium | Medium | 4 | 2-hr ramp-up per tool in S0; small spikes before full sprint commit
R4 | Job-search activity competes with build time | High | Medium | 6 | Log job apps INSIDE NOVA; turns competition into reinforcement
R5 | Job Opportunity Radar scraping breaks (site changes) | Medium | Low | 2 | API-first sources where available; graceful failure modes
R6 | Baicorp work crunch consumes capacity | Medium | Medium | 4 | 5 hr/day = ceiling, not floor; floor = 1 hr written reflection
R7 | Loss of motivation around Sprint 3 (the danger zone) | Medium | High | 6 | Sprint 3 deliverable intentionally visual (charts) for fast feedback

## Job Apps
Job Application Tracker
Log every Senior AI BA / AI BA / related application. Set 'NOVA referenced?' = Yes when you mention NOVA in cover letter / message / interview.
Date | Company | Role title | Source | NOVA referenced? | Status | Notes